## PJT-1
PROJECT-1 BMHA497L
MARL using Robot Swarms for Crop Monitoring and Precision Farming Applications |  | Project Start: | 2025-07-21
Dhinesh, Harshad, Sricharan |  | Today: | 2025-07-25
|  | Display Week | 1 |  |  | 2025-07-21 | [6 empty] | 2025-07-28 | [6 empty] | 2025-08-04 | [6 empty] | 2025-08-11 | [6 empty] | 2025-08-18 | [6 empty] | 2025-08-25 | [6 empty] | 2025-09-01 | [6 empty] | 2025-09-08
 | time axis 2025-07-21 to 2025-09-14
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2025-07-21 to 2025-09-14
PHASE 1-A: MARL Comparison Study [CONFERENCE]
Literature Study | All | 100% | 2025-07-21 | 2025-07-25 | 5
Selection and Assessment of MARL Algorithms | Harshad, Sricharan | 50% | 2025-07-23 | 2025-08-01 | 10
Training and Evaluation of Selected Algorithms | Harshad, Sricharan | 10% | 2025-07-24 | 2025-08-08 | 16
Creation and Testing of Optimal Environment | Harshad, Sricharan | 0% | 2025-08-04 | 2025-08-22
Formulation of Conference Paper | Harshad, Sricharan | 0% | 2025-08-18 | 2025-08-25 | 8
PHASE 1-B: Plant Disease Classification and Training
Collection of Image Datasets | All | 0% | 2025-08-25 | 2025-09-05 | 12
Training of Optimal ML Model | Dhinesh | 0% | 2025-09-01 | 2025-09-19 | 19
ML Model Evaluation | Dhinesh | 0% | 2025-09-15 | 2025-09-22 | 8
Selection of LLM and LSTM Prediction | Dhinesh | 0% | 2025-09-18 | 2025-09-26 | 9
Development of Web-App, Weather API and IndicBERT NLP | Dhinesh | 0% | 2025-09-22 | 2025-10-10
PHASE 2: Software Integration and Evaluation
Testing in ROS + Gazebo Environments | Harshad, Sricharan | 0% | 2025-10-13 | 2025-10-24 | 12
Fine-Tuning of LLM and Integration of APIs | Dhinesh | 0% | 2025-01-20 | 2025-01-31 | 12
Application of ML Model to Single Agent | All | 0% | 2025-10-24 | 2025-11-07 | 15
Final Testing of MARL and ML in Multi-Agent Environment | All | 0% | 2025-11-03 | 2025-11-12 | 10
PHASE 3: Hardware
BOM Assessment/Purchasing of Materials | All | 0% | 2025-11-17 | 2025-11-14 | -2
Design and Stress/Motion Study Analyses | All | 0% | 2025-11-15 | 2025-11-18 | 4
Assessment and Application of Communication Protocol | All | 0% | 2025-11-17 | 2025-11-21
Fabrication and Testing of Prototype | All | 0% | 2025-11-20 | 2025-11-24 | 5
Field Testing of Rover Swarm for Row Cultivation | All | 0% | 2025-11-25 | 2025-11-28
Evaluation and Formulation of Research Paper | All | 0% | 2025-11-28 | 31-11-25 | #VALUE!
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.